## Communication plan
Name / project code |  | Project 1/ABC |  |  |  | Creation date |  | 2022-05-04
Reference |  | Program PG01/Portfolio PF02 |  |  |  | Version date |  | 2022-05-04
Project manager |  | Mme.Dupont |  |  |  | Version number |  | V2.3
Service/Organisation |  | Marketing/ Company XY
ID | Communication action | Message | Communication goal | Communication channel | Frequency | Target (groups or stakeholders) | Responsible | Sending date | Deadline | Status
| Prepare access to project documentation | All project documentation (schedule, budget, progress, risks and problems ...) is up-to-date and accessible | All stakeholders have complete and up-to-date information on the project to engage them and facilitate decision-making | Intranet website | - | Key actors + Project stakeholders + Attentive actors | Project manager | 30/10/2022 | 05/11/2022 | Done
| Send the project report | Project review document (progress, alerts, elements if needed support ...) | Inform the sponsor of the progress of the project and ask for support if needed | Mail | Weekly | Project sponsor | Project manager | - | -
| Organize the project committee + Send the report of the meeting | Project committee presentation document (progress, risk review, collection of alerts, problems to be resolved, etc.) | Inform the project's progress committee, coordinate and synchronize, resolve hindering problems | Project committee meeting + CR par mail | Weekly | Project committee | Project manager
| Organize the steering committee + Send the report of the meeting | Copil presentation document (progress, alerts, elements if needed for arbitration and/or decision making ...) | Inform the project's progress committee and ask for arbitration or decision making if necessary | Steering committee meeting + CR par mail | Monthly | Comité de pilotage | Project manager (or the sponsor)
| Organize the standup meeting | Progress, problems encountered ... | Stand-up meeting is to discuss: - Completed tasks of the previous day - Problems encountered and their resolution - objectives for the day | Stand-up meeting | Daily | Project team | Project team
| Organize information meetings for subsidiaries | Status of the project for each subsidiary | Manage the expectations of each subsidiary and keep them informed of progress | Informational meeting | Monthly | Attentive actors | Project manager
| Organize the delivery process | Dispatch of project deliverables | Inform stakeholders and users of the delivery schedule, and their respective contents, so that they are ready for change | Mail, Informational meeting, Site intranet, Monthly newsletter | Quarterly | Key actors + Acteurs projet + Attentive actors + Passive actors | Project manager
Communication plan

## Groups
The audience is segmented into four main groups:
* Key actors (decision makers who influence the project)
* Project stakeholders (directly involved in the project)
* "Attentive" actors (interested in the results of the project)
* "Passive" actors (direct or indirect beneficiaries but not active)
Key actors | Project stakeholders | Attentive actors | Passive actors
ISD (Cécile Marchand) | Project manager | Logistics manager | users in subsidiaries
CFO (Ali Jama) | Business team | Marketing manager
Sponsor (Olivier Durand) | Architect | Managers of subsidiaries
Developers
Project acceptance team